Project outline

The idea is to create a small repository of public domain content from different countries, translated  into different languages, with translations made available under CC licences.

Additionally, the site could include other forms of content, like graphics, photographs, music recordings (of compositions in the public domain).

This content could potentially be remixed / mashed up; also, grassroots translation could be encouraged.

How many countries?

The initial idea is to have 3 European countries (Finland, Hungary, Poland) and 3 Asian (Taiwan, Singapore?, Japan?, China?). Should we include more countries? We also need to enquire whether we could have a country from Americas or the Middle East.

If we decide that each piece of content needs to be translated into all participating languages, the amount of translating quickly grows – which could be a problem. Unless we decided that everything need not be translated into all languages. Additionally, content could be translated into languages of countries that are not formally participating.

Work Programme

The table project should include following tasks (information in parentheses concerns funding of particular tasks – should we fund them from the grant, from other sources, or attempt to do for free?):

1. Content creation

- selection of content (no – maybe could be done through online polls / consultations?)

- translation of content (YES)

- digitalisation of additional content (graphics, photographs) (no – this is of secondary importance, should be easy to find partners willing to do this in exchange for reputation, like libraries)

- recording of music based on public domain compositions (yes – if there are sufficient funds)

- descriptions of works, artists, etc (YES)

(1b. Editing of content as a whole. One option is to present the content as a collection – this requires minimal editing. The other option is to mash up the content, at some point, into one whole. I see two possible mash-ups: 1) a multimedia presentation of text, sound, images; 2) a print volume of text and images. This might not be feasible since it means additional costs)

- Online service

We need a simple web platform to store and present the content. Beyond simple presentation, we certainly need some localisation functions and good metadata capability. Possibly other functionalities as well.

Should we use a ready-made solution (CC Mixter? Omeka? Wordpress?) or write it quickly from scratch in something like Rails or Django?

- Coordination of work.

Should we fund just 1-2 global coordinators, or also national coordinators, responsbile for overlooking content creation? (YES, funded)

- Public events.

A global series of events promoting the project. These should be funded from other sources or funded minimally – since they can probably be easily organized with local partners and small funding.

(5. Printed publication. One option would be to produce a volume of works based on this project, possibly the mash-up from 1b.)

THINGS to consider

- Should we try to build a small, „closed” form – which is more manageable with limited funding – or a project that's open: for instance to additional translations, new content, etc? (but requires funding in a long term perspective). Possibly we can start with a closed form, with a vision of where this project could go if succesful.

- What size of the collection is substantial enough – so that it doesn't look to small and unimportant? Should we focus on works from one author in each country, or provide a range of works?

- Should we experiment with translation, for instance doing parallel translation (PL-> FI, PL-> HU, PL->JP, etc.) and serial translation (PL → FI → HU → JP) and comparing the results?

- Should we encourage mashups of the works (poem → song, text / poem → animation, podcast, composition → recording, etc.)