CHAPEL HILL PUBLIC ARTS COMMISSION

306 North Columbia Street, Chapel Hill, North Carolina  27516-2124

T: 919.968.2888 X 377    F: 919.969.2063    E: info@chapelhillarts.org

www.chapelhillarts.org

COMMITTEE REPORT

Committee name: Self Portrait Project

Date submitted: 13 February 2004

Last meeting date: January 28, February 12, 2004

Attendees: Erica Rothman, Anita Wolfenden, Andrew Ross, Ginger Blakely, Jimmy Haynes, Mary Ruth, Jackie Helvey, Morgan Kenney, Debbie Meyer, Hollie Taylor, Janice Tyler, Laura Casey, Tori Ralston, Kate Billings

Summary of discussion(s): Each meeting has been divided into various agenda items: 1) brainstorming places to put brochures and posters; 2) media outlets for articles and PSA’s; 3) email newsletters that would take emailed “flyers”; 4) potential  groups that may be willing to have an artist come in and facilitate a Self Portrait workshop; 5) venues for portraits; 6) plans for the opening reception (at the CH Museum); 7) plans for a panel discussion in April; 8) procedures for taking in portraits, hanging portraits, picking up portraits.

I won’t go into all the details of the discussions and brainstorming. Here are some of the decisions made and/or decisions in progress:

- Media: The Independent will run a story by Debbie Meyer in the Front Page area. We hope that the CH Herald will also write a story. Kate has continued to send PSA’s to all local media. Erica contacted WUNC radio.

- There are several groups around town that plan to have Portrait workshops, including Cornucopia House, and hopefully Carol Woods.

- Exact exhibition venues won’t be determined until al entries have been received. Some venues are; CH Town Hall, CH Museum, Carrboro Town Hall, Century Center, downtown storefronts, ArtsCenter’s front gallery space, etc.

- The opening Reception will be Thursday, April 1 from 7-9pm at the CH Museum. We will have music, the committee will make a potluck reception (other food welcomed!), and Morgan will make a slide show out of all of the portraits received.

- The panel discussion will be either Wed., April 7th, or sometime the week of April 19th, from 7-8:30 pm. Our first choice for venue is the Hargraves Center. Second choice is a public school, perhaps Culbreth.

- We are still debating who would be good panel members.  Kate will be our moderator and will do a short presentation /introduction about the role of public art, and will introduce panel members. We have been considering various kinds of speakers: an art historian; a non-artist who has made a portrait; an artist; a journalist; a town official…

Action items for full commission to consider: We would appreciate suggestions for potential panel members.

Future action items: Firming up all the above open decisions.

Next meeting scheduled: Probably Tuesday, March 2nd at 5pm

Submitted by: Erica Rothman