Mulberry Tree Consulting

Chapel Hill Public Arts Commission Board Retreat

January 8, 2005

Next Steps: Programs

| WHAT Recommendations | HOW | WHO | WHEN All dates 2005 |
| --- | --- | --- | --- |
| Create guidelines for artists’ submissions | - Find examples of what other organizations do - Write guidelines | Betsy Anita, Kate, Susan, Dick | 1-10 Completed by 4-1 |
| Look into new exhibition venues and community building activities | - Hold a discussion to brainstorm ideas - Investigate parking lot gallery space | Colleen, Erica, Dick, Anita Kate to confirm date Janet | 1st week in February May |
| Coordinate Larry Kirkland’s next visit | -presentation to Town Council -build in time with Commission -manager’s office/ community outreach | Janet | Mid-late February |
| Talk about missions statement and how programs relate to mission (program examination) | Special meeting where all Commission members are invited | Kate will coordinate time | Before February Commission meeting |
| De-accessioning maintenance | Meeting to set up next steps | Kate, Anita, Betsy, Colleen | 2nd week in February at Library |
| % for Art fact sheet and brochure | - Share brochure with full Commission - Fact sheet produced | Janet will bring brochure Janet | 1-12 Fact sheet to committee in 10 days |

Next Steps: Structure

| WHAT Recommendations | # HOW | WHO | WHEN All dates 2005 |
| --- | --- | --- | --- |
| Create draft version of organizational structure presented at retreat | Create draft | Jen | 2-1 |
| Build in structure for updates in board meeting | Add to agenda; inform all who will participate | Kate | 1-12 |
| Update timeline of Commission highlights presented at retreat | Comments given to Kate Kate will revise | Kate | Comments by 1-10 |
| Clearly define roles and process | Discussion among Commission members | Jeff and Kate will put on agenda and lead | February Commission meeting |
| Update committee lists |  | Kate |  |
| Increase visibility of Commission | - Weave into the work that’s being done - Communications committee devises a list for ways to get name out to public | Debbie takes lead with Communications committee | February meeting |
| Consider how to involve more diverse representation of the public in the Commission’s work | Have a discussion | Erica and Jeff |  |